## Gantt Chart
Fase | Tugas / Aktivitas | Role | PIC | Status | W1 | [5 empty] | W2 | [5 empty] | W3 | [5 empty] | W4 | [5 empty] | W5 | [5 empty] | W6 | [5 empty] | W7 | [5 empty] | W8 | [5 empty] | W9 | [5 empty] | W10 | [5 empty] | W11 | [5 empty] | W12 | [5 empty] | W13 | [5 empty] | W14
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6
Sprint 0: Initiation | Requirement Gathering & Observation | PM | Wira | Completed
| Pembuatan Product Backlog | PM | Wira | Completed | bar: W3 1 to W3 6
| Penyusunan & Finalisasi Dokumen SKPL | PM | Wira | Completed | bar: W3 1 to W4 6
Sprint 1: Infrastructure | Sprint Planning 1 | PM | Wira | Completed | bar: W5 1 to W5 6
| Setup Database & Cloud Environment | SE | Syahmi | Completed | bar: W5 1 to W6 6
| Pembuatan REST API Dasar | SE | Syahmi | In Progress | bar: W6 1 to W7 6
| Desain UI Mockup Dashboard & Scanner | UI/UX | Abid | Completed | bar: W5 1 to W6 6
Sprint 2: AI & Validation | Sprint Planning 2 | PM | Wira | In Progress | bar: W8 1 to W8 6
| Implementasi CV (Auto-capture Logic) | SE | Syahmi | Completed | bar: W8 1 to W8 6
| Preparation: |  |  | Completed | bar: W8 1 to W8 2
| Setup library CV (OpenCV) |  |  | Completed | bar: W8 1 to W8 2
| Setup environment testing (kamera) |  |  | Completed | bar: W8 1 to W8 2
| Core Development: |  |  | Completed | bar: W8 3 to W8 4
| Deteksi area bukti bayar (edge detection / contour detection) |  |  | Completed | bar: W8 3 to W8 4
| Auto-capture saat terdeteksi stabil |  |  | Completed | bar: W8 3 to W8 4
| Image preprocessing: |  |  | Completed | bar: W8 3 to W8 4
Cropping otomatis | bar: W8 3 to W8 4
| Perspective transform (biar lurus) |  |  | Completed | bar: W8 3 to W8 4
Noise reduction & sharpening | bar: W8 3 to W8 4
| Optimization: |  |  | Completed | bar: W8 5 to W8 6
| Handling kondisi: Low light Blur Background berantakan |  |  | Completed | bar: W8 5 to W8 6
| Implementasi OCR (Text Extraction) |  |  | In Progress | bar: W9 1 to W10 6
| Preparation: |  |  | In Progress | bar: W9 1 to W9 2
| Pilih engine OCR: Tesseract / EasyOCR / Google Vision API |  |  | In Progress | bar: W9 1 to W9 2
| Setup dependency & testing awal |  |  | In Progress | bar: W9 1 to W9 2
| Core Development: |  |  | In Progress | bar: W9 2 to W10 3
| Integrasi OCR dengan hasil image dari CV |  |  | In Progress | bar: W9 2 to W9 3
| Ekstraksi teks |  |  | In Progress | bar: W9 2 to W9 3
| Post-processing |  |  | In Progress | bar: W9 3 to W10 6
| Cleaning hasil OCR: - Remove noise text - Format ulang (regex) |  |  | In Progress | bar: W9 3 to W10 4
| Normalisasi data (uppercase, trimming, dll) |  |  | In Progress | bar: W10 5 to W10 6
| Logika Validasi Rule-based | SE | Syahmi | In Progress | bar: W10 5 to W10 6
Sprint 3: Integration & UAT | Sprint Planning 3 | PM | Wira | Not Started | bar: W11 1 to W11 6
| Integrasi Frontend-Backend-AI | SE | Syahmi | Not Started | bar: W11 1 to W12 6
| System Integration Testing (SIT) | QA | Satya | Not Started | bar: W12 1 to W12 6
| User Acceptance Testing (UAT) di DTI | PM & QA | Wira & Satya | Not Started | bar: W13 1 to W13 6
| Bug Fixing & UI Optimization | SE & UI/UX | Syahmi & Abid | Not Started | bar: W13 1 to W13 6
Release & Closure | Finalisasi Laporan & Dokumentasi | PM | Wira | Not Started | bar: W14 1 to W14 6